## Tasks
| Andreja A | David C | Nayara C | Julie O | Alex T
D1 | x | x | x | x | x
Metadata |  |  |  | x
Grantt diagram |  | x
Task division | x | x | x | x | x
Risk management |  |  | x |  | x
Report | x | x | x | x | x
D3 assignement | x | x | x | x | x
Data cleaning |  |  |  | x | x
Descriptive analysis |  |  | x | x
PCA | x | x | x
MCA | x | x |  | x
D4 assignement | x | x | x | x | x
Association rules |  |  | x |  | x
Clustering | x |  |  |  | x
Profiling |  | x |  | x
Discriminant analysis | x |  | x
Decision Trees |  | x |  |  | x
Presentation preparation | x | x | x | x | x
Group Count | 10 | 11 | 11 | 11 | 11

## Risks
Risk | How to prevent | How to manage
A team member leaves the group | All task need to have more than one member assigned to it | Re-assign tasks to compensate workload
A member cant keep up with his/her task | More than one member in task. | Extra member gets involved and re-assign.
Previous task not completed fully | After each task, communicate and discuss the outcoumes | Update the previous task and check with the group
Inconsistent data through tasks | Common database | Server or drive backups
A team member has problems with oral presentations | Ensure communication within the group to detect the team members that will need assistance | Divide the oral presentation accordingly